## Feuil1
Week | Tasks | Difficulty | Time (Day)
2023-04-10 | Create spreadsheet of project plan | Easy | 1
| Create trello board | Easy | 1
| Create Git repo | Easy | 1
2023-04-16 | Replace the scaffolding code with the flask code | Medium | 2
| Ensure the app runs locally | Medium | 2
| Ensure the app runs in Cloud Shell | Medium | 2
2023-04-23 | Set up GitHub Actions | Hard | 3
| Add the GitHub Actions badge to the README | Medium | 1
| Create the App Service in Azure | Medium | 3
| Test the app running in Azure App Service | Medium | 1
2023-05-02 | Set up the Azure DevOps pipeline | Hard | 5
2023-05-05 | Create architectural diagram | Medium | 2
| Take screenshots steps | Easy | 3
| Document the proceess in github README | Medium | 4
2023-05-16 | Create demo video and post to YouTube | Hard | 5
Goals
Deploy CI/CD Project Flask
Q4 plan | Submit the project
Yearly plan | Review the code and ensure it still works